## Instructions
Instructions:
The intent of this document is to facilitate the Project Tailoring process by identifying deliverables that will be produced for a specific project. To complete this document, identify items that will be used by answering "Yes" in the "Deliverable for My Project?" column next to each deliverable.
The Request Type columns provide guidelines for each deliverable. “Required” means that the activity is required and an artifact must be produced for a specific Request Type.
Note: Any “No” answer for a required deliverable must be accompanied by the reason the document is not needed for this project.
In cases where specific deliverables aren't required, you, or your manager, have the responsibility for deciding if the deliverable is necessary. Certain “recommendations” are made to help with that decision.
If a "non Tyson" template is used for a specific deliverable, it must contain the same information identified on the PMO template.
The time to complete the checklist is during the “Structure (Tailor) the Project” activity in the Plan phase of the Project Management Cycle.

## Project Tailoring Checklist
Service/Work Request Number:
Request Description:
Project Leader:
| Deliverable for My Project? |  | Milestone | REQUEST TYPES (Work / Service)
|  |  |  | Work | Small | Medium | Large
|  |  |  | < 161 hrs | < 161 hrs | > 160 hrs and <= 1,000 hrs | > 1,000 hrs
|  |  |  | No CIR & < $10,000 | No CIR & < $10,000 | > $10,000 and <= $100,000 | > $100,000
|  |  |  | < 3 Team Members | < 4 Team Members | 4 - 10 Team Members | 10+ Team Members
|  |  |  | Not Cross-Functional unless EDI | 1+ Internal Orgs Impacted | 1+ Internal Orgs Impacted | 1+ Internal Orgs / any # of External Orgs Impacted
|  |  |  | 1 Existing App or System Impacted | 1 System Impacted | 1+ Systems Impacted | Complex System Dependencies
|  |  |  | WR is Required / All Others Optional | SR & Inv is Required / All Others Optional | Deliverables Checklist must be approved by IS Manager | Deliverables Checklist must be approved by PMO
|  |  |  | Bypass Workflow / Approvals in SRS | Bypass Executive Approvals in SRS
Deliverable |  | If No, State the Reason |  | Work | Small | Medium | Large | Approval Req'd
Project Management
WBS, Tasks and Project Estimates | Yes |  |  | Required | Required | Required | Required
Project Charter | Yes |  |  | Optional | Optional | Required | Required
Communication Plan | No |  |  | Optional | Optional | Required | Required
Project Schedule / Plan | No |  |  | Optional | Optional | Recommended | Required
Project Status Reports | No |  |  | Optional | Optional | Recommended | Required
Risk Assessment | No |  |  | Optional | Optional | Recommended | Required
Customer Surveys | No |  |  | Optional | Optional | Recommended | Required
Lessons Learned | No |  |  | Optional | Optional | Recommended | Required
Post Implementation Review | No |  |  | Optional | Optional | Recommended | Required
Investigate
Work or Service Request | No |  |  | Required | Required | Required | Required
Investigation | Yes |  |  | Optional | Required | Required | Required
Capital Investment Request (CIR) | No |  |  | Optional | Optional | Required for the following criteria: | Required for the following criteria:
[6 empty] | 1. For purchase of PP&E when useful life is > 1 year | 1. For purchase of PP&E when useful life is > 1 year
[6 empty] | 2. Extraordinary repairs that meet the 50/50 rule | 2. Extraordinary repairs that meet the 50/50 rule
[6 empty] | 3. Any repair > $10,000 | 3. Any repair > $10,000
[6 empty] | 4. Machinery & equipment > $3,000 | 4. Machinery & equipment > $3,000
[6 empty] | 5. Office equipment > $1,000 | 5. Office equipment > $1,000
[6 empty] | 6. Lease agreement where life > 1 yr and $1,000 | 6. Lease agreement where life > 1 yr and $1,000
[6 empty] | 7. Consulting services > $10,000 | 7. Consulting services > $10,000
Investigate Phase Gate Review | No |  |  | Coming Soon | Coming Soon | Coming Soon | Coming Soon
Analyze
Infrastructure Requirements | No |  |  | Optional | Optional | Required | Required
Data Modeling Requirements Guideline | No |  |  | Optional | Optional | Recommended | Required
Solution Requirements Guideline | No |  |  | Optional | Optional | Recommended | Required
User Requirements | No |  |  | Optional | Optional | Required | Required
Use Cases | No |  |  | Optional | Optional | Required | Required
Functional Requirements | No |  |  | Optional | Optional | Required | Required
User Acceptance Test Plan | No |  |  | Optional | Optional | Recommended | Required
Master Test Plan | No |  |  | Optional | Optional | Required for complex scope or large number of deliverables. Required for all new systems, database changes or changes involving multiple IS / Business groups. | Required
Analyze Phase Gate Review | No |  |  | Coming Soon | Coming Soon | Coming Soon | Coming Soon
Design
Technical or Design Specification: High-level architecture plus detailed guidance on how to implement the functions and features described in the requirements. | No |  |  | Optional | Optional | Required if pertinent | Required if pertinent.
Integration Test Cases and Scripts | No |  |  | Optional | Optional | Required | Required
User Acceptance Test Cases and Scripts | No |  |  | Required | Required | Required | Required
Internal Control Procedure | No |  |  | Optional | Optional | Required if a new internal control or a change to an existing control will be implemented. | Required if a new internal control or a change to an existing control will be implemented.
Training Plan | No |  |  | Optional | Optional | As Required by Master Org. Change Plan. | As required by Master Org. Change Plan.
Implementation Plan | No |  |  | Optional | Optional | Recommended | Required
Design Phase Gate Review | No |  |  | Coming Soon | Coming Soon | Coming Soon | Coming Soon
Construct
Program Code | No |  |  | Optional | Optional | Optional | Optional
Unit Test Cases and Scripts | No |  |  | Optional | Optional | Required if a Technical Specification is produced. | Required if a Technical Specification is produced.
Configuration | No |  |  | Optional | Optional | Optional | Optional
Converted Databases and Files | No |  |  | Optional | Optional | Optional | Optional
Test Data | No |  |  | Optional | Optional | Optional | Optional
Unit Test Results & Error Report | No |  |  | Optional | Optional | Optional | Optional
Construct Phase Gate Review | No |  |  | Coming Soon | Coming Soon | Coming Soon | Coming Soon
Test
Functional Test Results & Error Report | No |  |  | Optional | Optional | As required by Master Test Plan | As required by Master Test Plan
Integration Test Results & Error Report | No |  |  | Optional | Optional | As required by Master Test Plan | As required by Master Test Plan
User Acceptance Test Results & Error Report | No |  |  | Optional | Optional | As required by User Acceptance Test Plan | As required by User Acceptance Test Plan
Performance Test Results & Error Report | No |  |  | Optional | Optional | As required by Master Test Plan | As required by Master Test Plan
Parallel Test Results & Error Report | No |  |  | Optional | Optional | As required by Master Test Plan | As required by Master Test Plan
Go/No Go Checklist | No |  |  | Optional | Optional | Recommended | Required
Test Phase Gate Review | No |  |  | Coming Soon | Coming Soon | Coming Soon | Coming Soon
Implement
SOX 404 Checklist for Change Mangement | No |  |  | Required for all application changes submitted in TCMS. | Required for all application changes submitted in TCMS. | Required for all application changes submitted in TCMS. | Required for all application changes submitted in TCMS.
Support Plan | No |  |  | Optional | Optional | Recommended | Required
Miscellaneous
Project Change Orders | No | Any Phase |  | Optional | As Needed | As Needed | As Needed
Vendor Selection Process Checklist | No | Investigate Phase |  | Optional | Optional | Required when a vendor evaluation or selection process is required. | Required when a vendor evaluation or selection process is required.
Request for Information (RFI) | No | Investigate Phase |  | Optional | Optional | Required when a vendor evaluation or selection process is required. | Required when a vendor evaluation or selection process is required.
Request for Proposal (RFP) | No | Investigate Phase |  | Optional | Optional | Required when a vendor evaluation or selection process is required. | Required when a vendor evaluation or selection process is required.
Vendor Contract | No | Investigate Phase |  | Optional | Optional | Required for any agreement with a vendor. | Required for any agreement with a vendor.
Internal Controls Matrix | No | Analyze Phase |  | Optional | Optional | Required if a new internal control or a change to an existing control will be implemented. | Required if a new internal control or a change to an existing control will be implemented.
Training Effort Estimate | No | Analyze Phase |  | Optional | Optional | Required if organizational changes are expected e.g. those that are significant enough to require training. | Required
Audience Assessment | No | Analyze Phase |  | Optional | Optional | As required by Master Org. Change Plan. | As required by Master Org. Change Plan.
Job Impact Assessment | No | Analyze Phase |  | Optional | Optional | As required by Master Org. Change Plan. | As required by Master Org. Change Plan.
System and BPP Documentation (Training Materials) | No | Analyze Phase |  | Optional | Optional | As required by Master Org. Change Plan. | As required by Master Org. Change Plan.
Internal Controls Screen Shots | No | Test Phase |  | Optional | Optional | Required if controls were added or changed | Required if controls were added or changed

## PTC for Plant Controls
Service/Work Request Number:
Request Description:
Project Leader:
| Deliverable for My Project? |  | Milestone | REQUEST TYPES (Work / Service)
|  |  |  | Work | Small | Medium | Large
|  |  |  | < 161 hrs | < 161 hrs | > 160 hrs and <= 1,000 hrs | > 1,000 hrs
|  |  |  | No CIR & < $10,000 | No CIR & < $10,000 | > $10,000 and <= $100,000 | > $100,000
|  |  |  | < 3 Team Members | < 4 Team Members | 4 - 10 Team Members | 10+ Team Members
|  |  |  | Not Cross-Functional unless EDI | 1+ Internal Orgs Impacted | 1+ Internal Orgs Impacted | 1+ Internal Orgs / any # of External Orgs Impacted
|  |  |  | 1 Existing App or System Impacted | 1 System Impacted | 1+ Systems Impacted | Complex System Dependencies
|  |  |  | WR is Required / All Others Optional | SR & Inv is Required / All Others Optional | Deliverables Checklist must be approved by IS Manager | Deliverables Checklist must be approved by PMO
|  |  |  | Bypass Workflow / Approvals in SRS | Bypass Executive Approvals in SRS
Deliverable |  | If No, State the Reason |  | Work | Small | Medium | Large | Approval Req'd | Project Folder | Responsible
Planning
WBS, Tasks and Project Estimates | Yes |  |  | Required | Required | Required | Required | No |  | Project Leader
Project Charter | No |  |  | Optional | Optional | Required | Required | No |  | Project Leader
Project Schedule / Plan | No |  |  | Optional | Optional | Recommended | Required | Yes |  | Project Leader
Project Status Reports | No |  |  | Optional | Optional | Recommended | Required | No |  | Project Leader
Risk Assessment | No |  |  | Optional | Optional | Recommended | Required | No |  | Project Leader
Customer Surveys | No |  |  | Optional | Optional | Recommended | Required | No |  | Project Leader
Lessons Learned | No |  |  | Optional | Optional | Recommended | Required | No |  | Project Leader
Communication Plan | No |  |  | Optional | Optional | Recommended | Recommended | No | 3.2 | Project Leader
Post Implementation Review | No |  |  | Optional | Optional | Recommended | Required | No |  | Project Leader
Investigate
Work / Service Request | Yes |  |  | Required | Required | Required | Required | Yes | 6.1 | IS Manager
Investigation | No |  |  | Optional | Required | Required | Required | No | 6.2 | Analyst
Operations Standards Checklist | No |  |  | Optional | Required | Required | Required | No | Needs added to policy; rec 3.1 | Project Leader
External Vendor Required | No |  |  | Optional | Optional | Required when a vendor evaluation or selection process is required | Required when a vendor evaluation or selection process is required. | No |  | Project Leader
Capital Investment Request (CIR) | No |  |  | Optional | Optional | Optional | Optional | Yes | 6.4 | Project Leader
Investigate Phase Gate Review | No |  |  | Coming Soon | Coming Soon | Coming Soon | Coming Soon
Analyze
Infrastructure Requirements | No |  |  | Optional | Optional | Required | Required | Yes | 6.2 | Analyst
Data Modeling Requirements Guideline | No |  |  | Optional | Optional | Recommended | Required | Yes | 6.2 | Analyst
User Requirements | No |  |  | Optional | Optional | Recommended | Required | Yes | 6.2 | Analyst
Use Cases | No |  |  | Optional | Optional | Recommended | Required | Yes | 6.2 | Analyst
Functional Requirements | No |  |  | Optional | Optional | Recommended | Required | Yes | 6.2 | Analyst
Functional Specification | No |  |  | Optional | Optional | Required when the URD and FRD do not contain enough information to implement the design. | Required when the URD and FRD do not contain enough information to implement the design. | Yes | 7.1 | Analyst
Analyze Phase Gate Review | No |  |  | Coming Soon | Coming Soon | Coming Soon | Coming Soon
Design
Technical Specification | No |  |  | Optional | Optional | Required if pertinent. | Required if pertinent. | Yes | 8.1 | Technical Lead
Training Plan | No |  |  | Optional | Optional | Recommended | Recommended | Yes | 7.2 | Project Leader
Implementation Plan | No |  |  | Optional | Optional | Recommended | Recommended | Yes | 8.5 | Project Leader
Analyze Phase Gate Review | No |  |  | Coming Soon | Coming Soon | Coming Soon | Coming Soon
Construct
PLC Program | No |  |  | Optional | Optional | Required if pertinent. | Required if pertinent. | Yes | RSMACC | Programmer
HMI Program | No |  |  | Optional | Optional | Required if pertinent. | Required if pertinent. | Yes | RSMACC | Programmer
SCADA Program | No |  |  | Optional | Optional | Required if pertinent. | Required if pertinent. | Yes | RSMACC | Programmer
Construct Phase Gate Review | No |  |  | Coming Soon | Coming Soon | Coming Soon | Coming Soon
Test
Factory Acceptance Test Results (FAT) & Error Report | No |  |  | Required | Required | Required | Required | Yes | 10.3 | Project Leader
Site Acceptance Test Results (SAT) & Error Report | No |  |  | Required | Required | Required | Required | Yes | 10.3 | Project Leader
User Acceptance Test Results (UAT) & Error Report | No |  |  | Required | Required | Required | Required | Yes | 10.3 | Project Leader
Functional Test Results & Error Report | No |  |  | Optional | Optional | As required by Master Test Plan | As required by Master Test Plan | No | 10.1 | Project Leader
Test Phase Gate Review | No |  |  | Coming Soon | Coming Soon | Coming Soon | Coming Soon
Implement
Implementation Schedule | No |  |  | Optional | Optional | Required if pertinent. | Required if pertinent. | No | 8.5 | Project Leader
Miscellaneous
Project Change Orders | No | Entire Project |  | Optional | As Needed | As Needed | As Needed | No |  | Project Leader
Vendor Selection Process Checklist | No | Investigate Phase |  | Optional | Optional | Required when a vendor evaluation or selection process is required. | Required when a vendor evaluation or selection process is required. | No |  | Project Leader
Request for Information (RFI) | No | Investigate Phase |  | Optional | Optional | Required when a vendor evaluation or selection process is required. | Required when a vendor evaluation or selection process is required. | No |  | Project Leader
Request for Proposal (RFP) | No | Investigate Phase |  | Optional | Optional | Required when a vendor evaluation or selection process is required. | Required when a vendor evaluation or selection process is required. | No |  | Project Leader
Vendor Contract | No | Investigate Phase |  | Optional | Optional | Required for any agreement with a vendor. | Required for any agreement with a vendor. | No |  | Project Leader
Note on A51: Tyson Foods, Inc.: Added for version 1.2 and PMO approval May 31, 2 007
Note on A52: Tyson Foods, Inc.: Added for version 1.2 and PMO approval May 31, 2 007
Note on A53: Tyson Foods, Inc.: Added for version 1.2 and PMO approval May 31, 2 007